## Sheet1
Project: Movie Manager Application by |  | Members: Reid, Paul, and Schrein
Project Backlog
| Backlog Items | % Complete | Estimated Programming Time (HH:MM) | Actual Programming Time (HH:MM) | Estimated Difficulty (1 to 10) | Actual Difficulty (1 to 10)
Project:
| Create Windows Forms Application | 0% | 0:00 |  | 2
Main.cs Form:
| Create Main.cs | 0% | 0:01 |  | 8
| Add working MenuStrip control having all menu items | 0% | 0:00 |  | 4
| Add DataGridView control and write code to populate with movies list when the form first starts | 0% | 0:01 |  | 6
| Write code for Refresh menu item to populate DataGridView control on-demand | 0% | 0:01 |  | 8
About.cs Form:
| Create About.cs form. Test that it can be invoked from Main menu, and that it can be invoked as a dialogue | 0% | 0:00 |  | 2
| Add required text to RichTextBox control and code content display | 0% | 0:01 |  | 9
AddMovie.cs Form:
| Create AddMovie.cs form. Test that is can be invoked from Main menu | 0% | 0:00 |  | 2
| Code AddMovie to add new title to database. | 0% | 0:01 |  | 8
UpdateMovie.cs Form:
| Create UpdateMovie.cs form. Test that it can be invoked from Main menu | 0% | 0:00 |  | 5
| Code UpdateMovie's Find button to test whether a movie of a given title exists. | 0% | 0:00 |  | 5
| Code logic to fill-in controls on form with Movie data | 0% | 0:01 |  | 9
| Code logic to update/save changes to movie row in database. | 0% | 0:00 |  | 4
DeleteMovie.cs Form:
| Create DeleteMovie.cs form. Test that it can be invoked from Main menu | 0% | 0:00 |  | 2
| Test DeleteMovie's Find button to test whether a movie of a given title exists. | 0%
| Code logic to prompt user with dialogue box asking if they really wish to delete title. | 0% | 0:00 |  | 1
| Code logic to delete movie from from database. | 0% | 0:00 |  | 3
|  | Total Time: | 0:09 | 0:00