## Sheet1
Project: Movie Manager Application by |  | Members: Reid, Paul, and Schrein
Project Backlog
| Backlog Items | % Complete | Estimated Programming Time (HH:MM) | Actual Programming Time (HH:MM) | Estimated Difficulty (1 to 10) | Actual Difficulty (1 to 10)
Project:
| Create Windows Forms Application |  | 0.25
Main.cs Form:
| Create Main.cs |  | 1
| Add working MenuStrip control having all menu items |  | 0.5
| Add DataGridView control and write code to populate with movies list when the form first starts |  | 0.75
| Write code for Refresh menu item to populate DataGridView control on-demand |  | 1
About.cs Form:
| Create About.cs form. Test that it can be invoked from Main menu, and that it can be invoked as a dialogue |  | 0.25
| Add required text to RichTextBox control and code content display |  | 1
AddMovie.cs Form:
| Create AddMovie.cs form. Test that is can be invoked from Main menu |  | 0.25
| Code AddMovie to add new title to database. |  | 1
UpdateMovie.cs Form:
| Create UpdateMovie.cs form. Test that it can be invoked from Main menu |  | 0.5
| Code UpdateMovie's Find button to test whether a movie of a given title exists. |  | 0.5
| Code logic to fill-in controls on form with Movie data |  | 1
| Code logic to update/save changes to movie row in database. |  | 0.5
DeleteMovie.cs Form:
| Create DeleteMovie.cs form. Test that it can be invoked from Main menu |  | 0.25
Test DeleteMovie's Find button to test whether a movie of a given title exists.
| Code logic to prompt user with dialogue box asking if they really wish to delete title. |  | 0.15
| Code logic to delete movie from from database. |  | 0.25
|  | Total Time: | 3:36 | 0:00